STANDARD SUMMARY PROJECT FICHE

Project No. HU01XX

| 1. Basic Information |  |
| --- | --- |
| 1.1. Désirée no.: |  |
| 1.2. Title: | Promoting Social Integration of Disadvantaged Youth with Particular Emphasis on the Roma Minority, Phase II. |
| 1.3. Sector | Political Criteria |
| 1.4 Location | Hungary |

2. Objectives

2.1. Overall Objective

To promote social cohesion based on equal opportunity for minority groups with a differing social and/or cultural background, with particular emphasis on the Roma minority.

2.2. Project Purpose

- To decrease social distance between the majority population in Hungary and disadvantaged groups, especially Roma families

- 	To increase school enrolment and improve school success rates of socially disadvantaged and Roma youth at primary, secondary and higher education levels

- 	To improve opportunities for socially disadvantaged students and Roma students to access work opportunities in the labour market through educational and training pathways.

- 2.3. AP and NPAA priority

- AP 3.2 Medium-term Political Criteria: "Continue implementation of the medium-term Roma action programme."

- NPAA 2.1 Education and Training: "Improving social and educational conditions and the labour access of young people with multiple social disadvantages entering the labour market with no qualifications; implementation of training activities; development of necessary human resources."

- NPAA 2.1. c.1.4. Raising the level of schooling of people with multiple disadvantages: "The ensuring of equal opportunities for the Roma minority is impossible without raising the general standard of their schooling. … the Ministry of Education will consider continuing the HU-99.04-01 Phare project beyond 2002."

- 2.4. Contribution to the Preliminary National Development Plan

- This project contributes to the PNDP-priorities of improving employability and access to labour market of target groups facing difficulties and fighting against poverty.

- 2.5. Cross Border Impact

- Not applicable.

- 3. Description

- 3.1. Background and justification

- There are such kind of demographic changes in the Hungarian society that the number of the inhabitants is decreasing very fast and the society is growing old while the Roma population is getting younger that has to be taken into consideration. The proportion of children in the whole population is 5% this number exceeds 13% among the Roma people. The schools are not prepared to the special needs of the disadvantaged and Roma children, and there is a high proportion of disadvantaged youth leaving the school system without any qualification. Considering these facts there is a real danger of growing number of drop-out children and unemployment. The purpose of special educational programmes for disadvantaged children with particular emphasis on Roma minority is to improve the chances of academic success of children in rural or urban areas where the accumulation of social, cultural and economic disadvantages constitutes a barrier to successful schooling and a threat to future chances of employment and integration to the whole society.

The present project focuses on non-school-based elements, at the same time extending and further developing the Phare project HU9904-01. The intention is, on the one hand, to introduce new activities, which harmonise with and widen the previous programme, and on the other hand, to provide new opportunities for other eligible applicants (telecottages, Roma culture centres, civil organisations, special schools etc.) and for the winning or not-winning consortia of the previous project to launch or further develop their programmes.

In line with the European Union Policy Guidelines the project aims at developing the relationship between the majority of the society and the Roma minority in order to increase social cohesion. Its content was designed on the basis of Government Decree No. 1047/1999 on the Improvement of the Living Conditions and Social Position of the Roma Population (Sections 1., 2, 5 and 6).

Other important national education policy issues targeted by the present project are monitoring and quality management systems in the field of education. The White Book of Education Policy in Hungary is under construction and according to the plans, it will be in act from summer 2001. The policy includes new integrative programs and puts special emphasis on the integration and education of Roma minorities. Within the framework of the project programme development will start according to the Framework Curricula on the basis of Ministry of Education Decree No. 28/2000 (IX.21).

The Hungarian participation in the Community Initiative EQUAL was initiated by the Hungarian Government after the publication of the Community Communication published on 14.04.2000. The Hungarian Minister of Education sent a letter of intent to the European Commission's Employment and Social Affairs Directorate General, which was reflected positively by the Director General Ms. Odile Quintin. The Hungarian Ministry of Education elaborated a Draft Country Implementation Programme, and its chapter related to the labour market integration of socially disadvantaged people was approved as a part of the Hungarian National Phare Programme of 2001.

In line with the Guidelines of the Community Initiative EQUAL (Commission Communication 2000/C 127/02) the EQUAL Programme component aims to create Development Partnerships able to launch transnational projects in the field of combating racism and xenophobia in relation with the labour market (pillar “Employability” field (b) in the Guidelines).

- 3.2. Linked activities

- The proposed measure is partially a sequel to the sub-project "Secondary education of socially disadvantaged young people" of Phare programme HU9405 entitled "Strengthening the links between education and the economy”. Within that framework, Phare contributed to the improvement of the quality of education, continuing education and re-training better responding to the needs of the market economy.

- The social integration of disadvantaged youth and especially young Roma was the subject of Phare project HU9904-01. This project is currently in an advanced stage of implementation.

- Another linked activity is the ESF-type pilot project of the Ministry of Social and Family Affairs entitled “Improving the employability of socially disadvantaged groups”. Its immediate objective is reducing long-term unemployment of disadvantaged youth, people living with disabilities, and marginalised groups of the population with special emphasis on the Roma. Finally, the “Roma social integration” programme by the Office of National and Ethnic Minorities aims at improving the social and economic situation of the Roma, and as well co-operation and communication between the Roma and the institutions providing public services, thus diminishing social prejudices.

- 3.3. Results

- 	New and improved local educational, cultural, administrative and training services for socially disadvantaged and Roma population.

- 	New training programmes, mainly for Roma specialists launched; at least 40 mediators trained.

- 	Approximately 40 Information and Training Centres operating.

- 	Efficiency of settling official affairs increased, better relationship between the Roma minority and the majority of the society.

- 	Preventive actions implemented, thus school drop-out rate of socially disadvantaged and especially Roma children decreased.

- 	More socially disadvantaged and Roma children have better chances in entering secondary and higher education.

- 	Number of students completing their studies successfully in school increased.

- 	Innovative actions in the field of education and training in relation to access of the Roma to the labour Market tested and best practices verified in association with the relevant transnational partner.

- Best practices transferred into Government policy vis a vis the socially disadvantaged people, especially the Roma minority.

- 3.4. Activities:

- The project will be carried out through a range of three grant schemes each backed-up by a specific service contract. On overview of the planned activities is provided in the following table, which is followed by detailed information on the three schemes.

| - Type of Measure | - Activity Clusters | - Eligible Applicants | - Project Size - (in EURO) |
| --- | --- | --- | --- |
| - Grant Scheme - 1. | - Establishing new ‘Information and Training Centres’. | - Consortia of different type of institutions and/or organisations (e.g. Telecottages, Roma Community Houses, Roma Cultural Houses, Roma Information Centres, civil organisations, educational and training institutions, Regional Retraining Centres etc.) | - 100,000 |
| - Service 1. | - Providing training programme for mediators | - Training-providers | - 50,000 – 100,000 |
| - Grant Scheme - 2. | - 1) Adapting, developing and applying new special pedagogical programmes and alternative pedagogical methods for socially disadvantaged and Roma children including pupils of specialised schools for children with slow progress, low achievement and socially disadvantaged backgrounds. | - Consortia of different type of institutions (e.g. specialised schools for children slow progress, low achievement and socially disadvantaged backgrounds, Roma civil organisations, Family Supporting Centres, County Pedagogical Institutions etc.) | - Up to 150,000 |
|  | - 2) Developing and introducing the knowledge of Romology in Higher Education and Training especially for those people whose later jobs will involve interaction with Roma people. | - Consortia of different type of institutions (eg. higher education institutions, etc.) | - 50,000 – 150,000 |
| - Grant Scheme - 3. | - Pilot actions covering innovative ways of facilitating access of the Roma to the labour market through education and training pathways. | - The proposals will be presented by consortia (Development partnerships) bringing together institutions such as local authorities, local Roma minority self-government, local and regional training institutions (e.g. vocational education and training institutions, Regional Labour Force Training Centres, Regional Retraining Centres), local and regional labour offices, enterprises, NGOs, cultural organisations, employers organisations , trade unions etc. | - 500.000-700.000 |
|  | - Between 5 and 10% of the budget of Grant Scheme 3 will be set aside to finance the following actions: participation of the beneficiaries in the EQUAL thematic network, assistance to the beneficiaries in the preparation of the grant application, costs associated with project selection and monitoring. |  | - 100.000-200.000 |

- Grant Scheme 1.

- Grant Scheme 1. aims at and establishing Information and Training Centres (ITCs). Phare support will help these Centres to

- create the possibility for different generations of socially disadvantaged and especially Roma families to learn together,

- arrange official affairs and spend free time in a useful manner,

- provide education and training programmes for Roma children and adults e.g. in the form of courses, tutoring, remedial training, preparatory courses etc. (training aims will include the development of communication skills, and acquiring basic PC knowledge),

- support people with lower education to be able to get help from trained clerks in managing their official affairs

- facilitate the interaction between Roma people and the national and local authorities,

- provide useful resources for individual cultural activities, such as internet, books, video films etc.

- In order to secure an efficient use of Phare funds and existing national resources, the establishment of these Centres will be based on the already existing Network of Telecottages, Roma Community Houses, Roma Cultural Centres and Roma Information Centres where possible, but Phare support will also be used to extend this network by establishing new Information and Training Centres in the most disadvantaged regions. Any schools working on the basis of new pedagogical programmes aiming to fight school difficulties of disadvantaged youth and especially young Roma can benefit from the information resources, remedial training and infrastructural facilities of the ITCs'.

- Project proposals will include the ideas of the applicants concerning the concerning staff capacity, the ways they can reach Roma communities, necessary training programmes to be launched and the ways it could be organised etc.

- Duration of Grant Scheme 1: 09/2002-02/2004.

- It is foreseen to define the amount of the financial support per consortium in Grant Scheme 1 as min. 100,000 EURO.

- Service 1.

- Service 1. will provide the opportunity to train at least 40 mediators.

- The organisation of the Information and Training Centres must be done in parallel with the training of the mediators to provide help for socially disadvantaged people with managing their official affairs. In the project proposals submitted within the first Grant Scheme applicants will indicate their training needs related to the mediators, which will be a basic input for the Service Tender. Trainee mediators will receive relevant cultural, sociological, psychological and communicational knowledge with special emphasis on disadvantaged youth and Roma minority. The mediators will be trained to facilitate social interaction between the Roma minority and the majority population.

- The possible tasks of these specialists will involve e.g.: Keeping daily contact and having regular interaction with Roma communities and organisations getting them involved in the ITC system.

- Service 1. is to be co-financed from Phare and national contributions.

- Grant Scheme 2.

- 1) Grant Scheme 2. aims at supporting institutions working in the field of prevention, such as specialised schools for children with slow progress, low achievement and socially disadvantaged backgrounds, to adapt, develop and apply new special pedagogical programmes and alternative pedagogical methods for the target group (socially disadvantaged and Roma children). These schools could not participate in the previous Phare programme, because of their special educational position. However there is a high number of children learning at these special schools, who belong to the target group due to their socially disadvantaged background. With the help of these programmes these children could be redirected to regular educational institutions to finish their primary education successfully.

- 2) Developing and introducing the knowledge of Romology in higher education and training especially for those people whose later jobs will involve interaction with Roma people. This project would allow consortia including higher education institutions to develop new modules and participate in the suppression of prejudice in all segments of society. This could include the education of police, lawyers, public servants, teachers, etc.

- Duration of Grant Scheme 2: 02/2002-02/2004

- It is foreseen to define the amount of the financial support per consortium in Grant Scheme 2 as min. 50,000 EURO and as max. 150,000 EURO.

- Grant Scheme 3.

- Grant Scheme 3 is intended to support pilot actions in the field of education and training to promote access of the Roma to the labour Market. This will be done by piloting the Community initiative EQUAL. The project fits clearly the first of the thematic areas of the EQUAL initiative (Employability):

- At the beginning of the project a call for proposal will be issued for pilot actions covering innovative ways of facilitating access of the Roma to the labour market.

- The proposals will be presented by consortia (Development partnerships) bringing together institutions such as local authorities, local Roma minority self-government, local and regional training institutions (e.g. vocational education and training institutions, Regional Labour Force Training Centres, Regional Retraining Centres), local and regional labour offices, enterprises, NGOs, cultural organisations, employers organisations , trade unions etc.)

- The selected Development partnership will have to propose as part of their activities a component covering transnational co-operation with (a) Development partnership(s) financed under the EQUAL initiative in the meber states.

- The total budget for this component will be 2 MEURO (joint Phare and Government co-financing). It is expected that between 3 and 4 DPs will be financed under the project.

- Duration of Grant Scheme 3: 01/2002-02/2004

- It is foreseen to define the amount of the financial support per consortium in Grant Scheme 3 as min. 500.000 EURO and as max. 700.000 EURO.

- Between 5 and 10% of the budget Grant Scheme 3 will be set aside to finance the following actions: participation of the beneficiaries in the EQUAL thematic network, assistance to the beneficiaries in the preparation of the grant application, costs associated with project selection and monitoring.

- 4. Institutional Framework:

Implementing Agency: European Social Fund National Implementing Agency, established by the Ministry of Economics, Ministry of Social and Family Affaires and the Ministry of Education.

Ministry of Education: takes professional responsibility of the implementation and evaluation.

Regional Development Agencies: Undertakes the task of day-to-day technical management of implementation of projects and monitoring activities under the authority of the IA. The relationship between the IA and the Intermediary (Regional Development Agency) shall be defined in a Cooperation Agreement.

- See the "Template for the Institutional Framework / Implementation Arrangements in Case of Grant Schemes" in Annex 5.

- 5. Detailed Budget (in EURO Million)

| - Component | - Phare Support |  |  | - National Co-financing | - IFI | - TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
|  | - Investment - Support | - IB | - Total Phare (=I+IB) |  |  |  |
| - Grant Scheme 1. |  | - 2.000 | - 2.000 | - 2.000 |  | - 4.000 |
| - Grant Scheme 2. |  | - 1.750 | - 1.750 | - 1.750 |  | - 3.500 |
| - Grant Scheme 3. |  | - 1.000 | - 1.000 | - 1.000 |  | - 2.000 |
| - Service 1. | - - | - 0.050 | - 0.050 | - 0.050 |  | - 0.100 |
| - Participation in thematic network, project preparation and monitoring |  | - 0.200 | - 0.200 | - 0.200 |  | - 0.400 |
| - Total |  |  | - 5.000 | - 5.000 |  | - 10.000 |

- 6. Implementation Arrangements

- 6.1 Implementing Agency (IA)

- The project will be implemented under the overall professional co-ordination and supervision of the Ministry of Education and in full agreement with regional actors. The ESF Implementing Agency (IA), established by the Ministry of Economy, the Ministry of Education and the Ministry of Social and Family Affairs, replacing the earlier Phare Programme Management Unit, will be responsible for the technical management and administration of programme implementation.

- PAO: Ms. Judit Juhász Bátkiné

- IA: ESF IA (Budapest, Professzorok Háza, Ajtósi Dürer sor. 19-21.)

A Steering Committe will be established to monitor project activities and provide guidance as appropriate. The SC will be chaired by the MOE and include, NAO, ESF Agency, Office for Ethnic minorities, Roma Self Government, EC Delegation and other relevant bodies.

6.2. Twinning

not applicable

6.3. Non- standard aspects

The rules of the Practical Guide will be strictly followed.

6.4 Contract

Three Grant Schemes:		EURO 9.5 Million

One service contract:		EURO 0.1 Million

Preparatory actions:		EURO 0.4 Million

7. Implementation Schedule

| Component | Start of Tendering | Start of Project Activity | Project Completion |
| --- | --- | --- | --- |
| Grant Scheme | 01/2002 | 09/2002 | 06/2004 |
| Service | 11/2001 | 06/2002 | 06/2004 |

8. Equal Opportunity

The national authorities involved are equal opportunity employers. Individual grants will be awarded according to equal opportunity principles.

9. Environment

The project makes a positive impact on the environment in an indirect way. On condition that Grant Scheme 1 and 2 are successfully implemented, the environment consciousness of the target group will be considerably increased through the Information and Training Centres and in schools.

10. Rates of Return

Not applicable.

11. Investment Criteria

n.a.

12. Conditionality and Sequencing

In case of Grant Scheme 1 and 2 the grant scheme and the tendering activity can start simultaneously. The Ministry of Education and all the participating organisations will provide for the human resources necessary for the timely implementation of all the planned operations.

In Grant Scheme 3 the future Development Partnerships have to prepare their working programme in 6 months. After 1 year of the working programmes' implementation the DPs are invited to create and take part in international networking.

Annexes to Project Fiche

- Logical framework matrix in standard format

- Detailed implementation chart

- Contracting and disbursement schedule

- Detailed Cost Breakdown

- Template for the Institutional Framework / Implementation Arrangements in Case of Grant Schemes

- Relation Of The Project With Previous Phare Activities

7. Reference to feasibility /pre-feasibility studies

8. List of relevant Laws and Regulations

9. Resumé of the Community initiative EQUAL

| Annex 1 to Project Fiche LOGFRAME PLANNING MATRIX FOR Project Social Integration Of Disadvantaged Youth With Particular Emphasis On The Roma Minority, Phase II |  |  | Programme name and number | Roma Phase II HU01xx |
| --- | --- | --- | --- | --- |
|  |  |  | Contracting period expires: June 2003 | Disbursement period expires June 2004 |
|  |  |  | Total budget : € 10.0 Million | Phare budget : € 5.0 Million |
| Overall objective | Objectively verifiable indicators |  | Sources of Verification |  |
| Social cohesion based on equal opportunity for minority groups with a differing social and/or cultural background, with particular emphasis on the Roma minority. | - Education and employment indicators for minority groups, especially the Roma population approach Hungarian regional and/or national averages |  | - Research on socially disadvantaged groups and the Roma population - Education and labour market studies |  |
| - Project purpose | - Objectively verifiable indicators |  | - Sources of Verification | - Assumptions |
| - Decreasing social distance between the majority population in Hungary and disadvantaged groups, especially Roma families -  School enrolment of socially disadvantaged and Roma youth improved at primary, secondary and higher levels - Growing number of socially disadvantaged students and Roma students complete their school studies successfully | - Discriminatory practices against minority groups come to light and decrease. - Higher number of effectively working local consortia - Better relationship between schools and minority group families - Increased number of Roma students in the vocational education - Number of target group drop-outs decreased and enrolment rates up in all participating schools - Number of target group graduates measurably increased |  | - Reports of the Roma National Self-government and Roma minority organisations - School enrolment and graduation data collected each year. - Statistics of the supported schools, project monitoring reports. - Data on students supported in the programme, report of vocational schools, project monitoring reports | - Acceptance of a certain level of positive discrimination both by the majority and by the Roma community. - Social/ethnic tolerance in local communities. - support of local/regional authorities. |
| - Results | - Objectively verifiable indicators |  | - Sources of Verification | - Assumptions |
| -  New and improved information services available for socially disadvantaged groups and Roma population - Training programme successfully completed -  New pedagogical models successfully introduced -  Development Partnerships created | - Audio-visual multimedia packages to promote labour market integration - 40 Information and Training Centres operating, at least 40 mediators trained - For or five Development Partnerships established |  | - Figures of the schools, project evaluation reports. - School statistics on the success rate of former drop-outs, project monitoring reports. - reports of vocational schools, project monitoring reports. | - Efficient co-operation between primary schools and vocational schools - Trained mediators are retained for assignments as planned - Funding of the operations available when required |
| - Activities | - Means |  |  | - Assumptions |
| - Establish new ‘Information and Training Centres’ - Provide training programme for mediators - Introduce new pedagogical models to schools to reduce drop-out rate of socially disadvantaged children - Support organisations for social integration of highly disadvantaged youth. - Develop and introduce the knowledge of Romology in Higher Education and Training - Create Development Partnerships following the EQUAL Community Initiative guidelines | - Three Phare Grant Schemes concerning organisation, training, and communication advice - One co-financed Phare Service Contract, two locally funded Service Contract |  |  | - Appropriate response by the target groups to the measures of the programme - Co-financing available as and when required |
|  |  | Preconditions |  |  |
|  |  | - Appropriately staffed unit for technical management of the project |  |  |

Annex 2

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

DETAILED IMPLEMENTATION TIME-CHART

|  | 2001 |  |  |  |  |  | 2002 |  |  |  |  |  |  |  |  |  |  |  | 2003 |  |  |  |  |  |  |  |  |  |  |  | 2004 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J |
| Components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grant Scheme 1. | D | D | D | D | D | D | T | T | T | T | T | T | T | T | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |
| Grant Scheme 2. | D | D | D | D | D | D | T | T | T | T | T | T | T | T | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |
| Grant Scheme 3. | D | D | D | D | D | D | T | T | T | T | T | T | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |
| Service 1. | D | D | D | D | D | D | T | T | T | T | T | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |

| Design | D |
| --- | --- |
| Tendering and Contracting | T |
| Contract Implementation and Payments | I |

Annex 3

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

CUMMULATIVE CONTRACTING AND DISBURSEMENT SCHEDULE (EURO MILLION)

| Date | 2001 |  | 2002 |  |  |  | 2003 |  |  |  | 2004 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 30/09 | 31/12 | 31/03 | 30/06 | 30/09 | 31/12 | 31/03 | 30/06 | 30/09 | 31/12 | 31/03 | 30/06 |
| Contracted (Grant) | 0 | 0 | 0 | 0 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 |
| Contracted (Service) |  |  |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |
| Disbursed | 0 | 0 | 0 | 0 | 0 | 1.0 | 2.5 | 3.0 | 3.2 | 4.2 | 4.5 | 5.0 |

Annex 4

.

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

DETAILED COST BREAKDOWN*

(Million EURO)

| Description | Phare | Central (Ministry of Education) | Total |
| --- | --- | --- | --- |
| Grant Scheme 1 | 2.000 | 2.000 | 4.000 |
| Grant Scheme 2. | 1.750 | 1.750 | 3.500 |
| Grant Scheme 3. | 1.000 | 1.000 | 2.000 |
| Service 1. | 0.050 | 0.050 | 0.100 |
| Participation in thematic network, project preparation and monitoring | 0.200 | 0.200 | 0.400 |
| Total: | 5.000 | 5.000 | 10.000 |

Annex 5

Template for the Institutional Framework /

Implementation Arrangements in Case of Grant Schemes

- IA (Implementing Agency): Retains full responsibility for programme implementation

- Intermediary: Undertakes the task of day-to-day technical management of implementation of projects and monitoring activities under the authority of the IA. The relationship between the IA and the Intermediary (Regional Develiopment Agency) shall be defined in a Cooperation Agreement which will reflect the institutional framework given in this fiche.

- Rules, procedures and formats: The grant section of the Commission Practical Guide will be strictly followed.

- Preparation of the package of call for proposal, guidelines for applicants and application form according to the practical guide

- IA drafts the call for proposal, the guidelines for applicants and the application form in consultation with the entities concerned in the given field (at national – e.g. Ministries - and regional level)

- IA submits the final version of the documents to EC for approval

- EC Delegation endorses the documents

- Publication of the call for proposal

- The IA takes all appropriate measures to ensure that the nationally and regionally publicised call for proposal reaches the target groups in line with the requirements of the Practical Guide.

- Project selection process

- RDA collects and registers incoming project proposals

- The IA selects (in agreement with the co-financing ministry/ies involved, if relevant) and approves the assessor team for the assessment of administrative compliance, eligibility and assessment of technical and financial quality of proposals

- The IA (PAO) nominates the evaluation committee (non-voting chairman and secretary, and voting members) with the co-financing ministry/ies involved, if relevant

- The IA nominates the members of the assessment team and evaluation committee exclusively on the basis of technical and professional  expertise in the relevant area

- The Delegation endorses the team of assessors and the composition of the evaluation committee. The Delegation nominates an observer to follow all or part of the proceedings of the Evaluation Committee. Prior approval is needed from the Delegation for the participation of other observers

- The evaluation committee draws up its recommendations and decisions according to the assessor team's written assessment of each proposal on the basis of the published evaluation grid

- The PAO approves the evaluation report prepared by the evaluation committee and forwards the evaluation report and any award proposals to the Delegation

- The Delegation endorses (ex-ante) the evaluation report on the selection process and the final list of grants to be awarded

- The IA notifies each applicant in writing of  the result of the selection process

- Contracting (PAO designated in the responsible implementing agency)

- The format of the grant contract is drafted according to the Practical Guide using the standard grant contract format and its annexes

- The format of the grant contract is to be approved by the Delegation (in cases where the call for proposals results in the award of a large number of grants which all have the same grant contract conditions)

- The PAO signs the grant contracts with the selected beneficiaries based on the final list of grants approved by the Delegation. The language of the grant contract is English and the official Hungarian translation of the contract is attached to the signed English language contract

- In case of a scheme which results in a small number of larger grant contracts (defined as those with a Phare contribution of over 300.000) the Delegation endorses the individual contracts (after its signature by the PAO and the beneficiary)

- Copy of the signed grant contract is sent to the Delegation

- Implementation of the selected projects by the beneficiaries

- Beneficiaries subcontract suppliers of goods, services or works, in line with Phare procurement regulations annexed to the Grant Contract and under the Practical Guide

- Projects under 300.000 Euro (Phare contribution) will be subject to ex-post control by the EC Delegation pursuant to the Practical Guide

- Tender documents and contracts above 300.000 Euro (Phare contribution) will be subject to the ex-ante endorsement of the EC Delegation pursuant to the Practical Guide

- Financial management of the selected projects

- The IA with the technical assistance of the RDA receives and verifies the invoices and requests payment by the National Fund

- Monitoring of the projects implemented by the beneficiaries

- Standard Phare monitoring instruments will be used for monitoring purposes. Attention is drawn to the special duty of the RDA with regard to the day-to-day monitoring of the selected projects.

The amount of support for each consortium will not exceed 300,000 EURO.

Annex 6

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

RELATION OF THE PROJECT WITH PREVIOUS PHARE ACTIVITIES

Phare Project HU 94-05 “Strengthening the links between education and economy”

The subproject entitled Secondary education of socially disadvantaged young people in this former Phare project can be regarded partly as a precedent to this planned project. The project was the first step in contributing to the improvement of the quality of education, continuing education and re-training courses corresponding to the training needs of the economy.

The Phare Project HU-99.04-01 “Social Integration of Disadvantaged Youth, with Particular Emphasis on the Roma Minority” aims at the social integration of disadvantaged, especially Roma youth. Specific objectives are the reduction of the primary school drop-out rate, facilitating the access of Roma students to secondary and vocational education, as well as support preparing talented young Roma students for higher education.

ESF type pilot project of the Ministry of Social and Family Affairs entitled “Improving the employability of socially disadvantaged groups”. The objective of the HR development projects to be implemented in the regions listed in the Preliminary Regional Development Plans is promoting the labour-market chances of socially disadvantaged groups, especially the Roma.

“Roma social integration” programme by the Office of National and Ethnic Minorities promoting the social integration of and securing equal rights and opportunities for the Roma minority.

# Annex 7

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

# REFERENCE TO FEASIBILITY STUDIES

- Secondary education for socially disadvantaged youth. Hegedüs (ed.), Study supported by the Phare Programme HU-94.05., Budapest, 1998.  (in print)

- Transition from initial education to working life. OECD Study. Analysis of the education/training system in Hungary (with particular emphasis on its relevance to the market economy) focusing on the economic and social background, unemployment of young people, learning methods, educational and employment policies. 1998.

- Vocational Education and Training Reform in Hungary. European Training Foundation. Luxembourg, 1997.

- Education in Hungary. J. Lannert, National Institute of Public Education, Budapest, 1997.

- Report on the Vocational Education and Training System in Hungary. European Training Foundation, 1996

- Reviews of National Policies for Education. Hungary. Centre for Co-operation with Economies in Transition, Paris 1995

- Chapter on School Education. Background Report of the OECD Education Policy Review, G. Halász, National Institute of Public Education, Budapest, 1993.

Annex 8

Social Integration of Disadvantaged Youth

Project Fiche No. HU-0101

LIST OF RELEVANT LAWS AND  REGULATIONS

Public Education Act LXXIX of 1993 modified by LXXI (1995)

Modified Education Act in unified structure LXII (1996), defining the National Basic Curriculum (NAT)

In 1999 the Hungarian government has amended its 1997 mid-term package of measures aiming at the improvement of the living conditions of the Roma population with a government decision The government decision puts a particular emphasis on supporting the disadvantaged, especially the Roma youth so as to promote their social integration through education and training.

One of the most important measures to give substance to this programme has been the 1047/1999 (05.05) Government Decision on the Improvement of the Life Conditions and Social Position of the Roma Population.

Annex 9

Resumé of the Community initiative: EQUAL

1) OBJECTIVE

To develop cooperation between the Member States with a view to promoting new ways of combating all forms of exclusion, discrimination and inequalities in the labour market.

2) COMMUNITY MEASURE

Communication project from the Commission to the Member States of 13 October 1999 establishing the guidelines for Community initiative programmes for which the Member States are invited to submit applications for aid under the EQUAL initiative.

3) CONTENTS

1. The Community initiative EQUAL, inaugurated by Commissioner Anna Diamantopoulou on 14 April 2000, is one of four new initiatives adopted under Regulation No 1260/1999 containing general provisions on the Structural Funds for the period 2000-2006.

2. The Community initiative EQUAL, which is financed by the European Social Fund (ESF), forms part of a coordinated employment strategy provided for by the Treaty of Amsterdam which is based on the employment guidelines and, more specifically, the following four pillars: capacity for occupational integration; entrepreneurship; flexibility; equal opportunities.

3. In order to achieve a higher rate of employment in the European Union, the European employment strategy must henceforth be implemented at a lower level i.e. regional and local, which requires the initiatives to be coordinated. The Commission is aware of the added value of such a synergy and will ensure that the approach is geared towards cooperation and transnational action.

4. Moreover, previous projects too often produced too little employment because businesses were not involved sufficiently. The aim now is therefore to ensure that employers, even the smallest, take a greater part in the political process. Good practice must be spread more widely by local or sectoral partnerships. There are valuable lessons to be learned from the EMPLOYMENT and ADAPT programmes about the approach which needs to be adopted for the EQUAL initiative.

5. The EQUAL initiative implements the Community strategy for combating discrimination and social exclusion in the labour market. Its key aims are equal opportunities for men and women, the circumstances to which asylum seekers are exposed and the fight against racism at work. This approach is fully in line with the four pillars of the coordinated employment strategy and also allows a more specific approach to be taken on occasion under the fourth pillar (equal opportunities).

6. The first call for projects is for action under the following pillars:

Capacity for occupation integration (pillar I):

to ease access and return to the labour market in order to promote a labour market which is open to everybody;

to combat racism at work.

Entrepreneurship (pillar II):

to make it possible for anyone to start up a business;

to enhance the quality of employment in the social economy.

Flexibility (pillar III):

to develop practices for integrating people at work and for ongoing occupational training;

to introduce information technology, anticipate change and upgrade qualifications.

Equal opportunities for women and men (pillar IV):

to develop new forms of organisation of work to reconcile family and working life;

to reduce the gender pay gap and combat job segregation.

Each Member State will be asked to choose at least one field under each pillar for implementing the EQUAL initiative. The list of fields will be reviewed every two years.

7. The initiative's geographical and sectoral approach will be reflected in two types of development partnerships. Geographic development partnerships will involve economic players who are likely to have common interests in a given area. The development partnerships will give them an opportunity to meet and to devise a strategy for solving common problems. Sectoral partnerships will be geared to combating inequality and discrimination. The Member States will be free to choose the type of partnership involved.

8. In order to obtain funding under the EQUAL initiative, a development partnership in a Member State must cooperate with at least one other partnership in another Member State, generally funded by the EQUAL initiative too. Partnerships are also possible with a non-Member State eligible for funding under the Phare, Tacis or Meda programmes. The partnership's work programme must cover a period of between 18 months and three years.

9. All the Community initiative programmes must provide for three types of specific action which generate added value. First, they must result in development partnerships and transnational cooperation. Second, the development partnerships' work programmes must be implemented. Finally, thematic networks must be established, good practice spread and the impact on national policy assessed.

10. Technical assistance, the budget for which must not exceed 5% of the cofunding of the CIP by the ESF, will support implementation of the three courses of action. A database of best practice will be set up under the initiative.

11. The calls for proposals will be made in 2000, 2002 and 2004.

12. The Commission will set up an assessment system.

13. The EQUAL initiative will be funded jointly by the Member States and the European Community. The overall contribution of the ESF to this initiative between 2000 and 2006 is estimated at EUR 2 847 billion.

4) REFERENCES

Communication from the Commission COM(1999) 476 final 
Not published in the Official Journal

Opinion of the Committee of the Regions 
Official Journal C 156, 06.06.2000

5) FOLLOW-UP WORK

On 14 April 2000, the Commission presented a communication to the Member States establishing the guidelines for the Community Initiative EQUAL concerning transnational cooperation to pomote new means of combating all forms of discrimination and inequality in connection with the labour market 
[C(2000) 853 - Official Journal of 05.05.2000].

On 24 May 2000, the Commission adopted the Decision on granting a contribution from the European Social Fund to finance a group of actions under a global grant, implementation is in accordance with community assistance laid down in the context of the Social Funds (Actions of Article 6 (1)e.) of Regulation (EC) No 1784/99 of the European Parliament and of the Council of 12 July 1999.